InPlace

Development Roadmap

On-Demand Care Coordination Platform

Current Version: v1.15.1  |  Last Updated: February 22, 2026

# Guiding Principles

1. Ease of change first — Every structural decision makes the next change cheaper and safer.

2. Expand future capabilities — Build the foundation that makes advanced features possible without rewrites.

3. Demo-ready at all times — yourinplace.com must always work as a polished demo for investors.

# What’s Live Now (v1.15.1)

The production app at yourinplace.com includes all features through v1.15.1:

- Three user roles: Family (Pete), Caregiver (Maria), Care Recipient (Betty)

- Dual-role system: users can hold multiple roles (e.g., family + caregiver)

- Real-time WebSocket messaging, activity feed, visit photo uploads

- Care team CRUD with email invites, member management, shared care recipients

- Location-based caregiver search (Nominatim geocoding + Haversine radius)

- Caregiver onboarding wizard (5 steps), admin invite system

- Care request system (Betty requests help → caregiver accepts)

- Dynamic Help/FAQ page with admin management and deep-link navigation

- PWA installable on iOS, Android, and desktop with offline support

- Floating feedback button on all pages, admin feedback review panel

- Medical care disclaimer, email verification, 2FA, trusted devices

- 64 feedback items collected from real users driving roadmap priorities

# Next Up

v1.16.0 Admin Polish & Quick Wins Target: Feb 2026 ¦ NEXT

Address fresh feedback, improve admin panel, fix visible bugs.

- Admin stats exclude demo data (sessions count includes demo)

- Admin 2FA/biometrics gate for destructive actions

- Merge waitlist + invites into unified "People" tab

- Show app version on login screen; auto-include in feedback

- Caretaker signup inline field validation (replace generic error)

- Care request visible on family calendar

- Fix Invalid Date on activity feed + Betty’s calendar

v1.17.0 Caregiver Onboarding Completion Target: Mar 2026 ¦ PLANNED

Complete the caregiver registration experience.

- Pets/allergies/medical conditions in onboarding (all roles)

- Multiple certifications (dynamic list)

- Registration disclosures & agreements (background check, tax, terms)

- Remove availability from signup; add work zip + travel radius

- Stoplight chart: green/yellow/red task categorization

- Care recipient photo upload (thumbnail → full size)

v1.18.0 Stripe & Background Checks Target: Mar 2026 ¦ PLANNED

Enable payments. Blocked on Pete’s Stripe + Checkr setup.

- Stripe Elements for background check payment during onboarding

- Checkr API integration for background check submission + webhooks

- Stripe Connect marketplace (20% platform fee, destination charges)

- ACH standard free; instant payout ~2% fee (worker opts in)

- Caregiver earnings dashboard + family billing

v1.19.0 Availability & Scheduling UX Target: Apr 2026 ¦ PLANNED

- Interactive drag-to-select availability calendar (Outlook-style)

- Caregiver work location zip code + AreaMap centering fix

- Maria’s calendar color/block overlap fix

v2.0.0 Connections & Messaging Target: Apr 2026 ¦ PLANNED

- Connection request flow (search by email, accept/decline)

- Connection status persistence ("pending" visible in messages)

- Message push deep-links to conversation

- Video chat — Meet link in messages

- PWA back swipe navigation (in-app history stack)

v2.1.0 Dashboard & CaretakerHub Overhaul Target: May 2026 ¦ PLANNED

- CaretakerHub stat card drill-downs

- Push notification expansion + debug existing flow

- Care team member UX overhaul (card-based, options on click)

- Block user with evidence logging for legal

# Completed Versions

v1.15.0–1.15.1 Help/FAQ, Onboarding Fix & Demo Fixes February 22, 2026 ¦ COMPLETED

- ✓ Dynamic Help/FAQ page with 20 seed articles, role-based visibility, deep-link navigation

- ✓ Admin help management (CRUD, publish/unpublish, "Create FAQ from feedback")

- ✓ Fixed onboarding status endpoint (non-existent column references)

- ✓ Fixed demo account switching (stale activeRole, component key remount)

- ✓ Branding icons updated: Maria 🤝, Betty 🌷

- ✓ Seed roles column + DEMO_SEED_VERSION bumped to 1.15.1

v1.14.0 Dual-Role System February 22, 2026 ¦ COMPLETED

- ✓ Users can hold multiple roles (family + caregiver)

- ✓ "Add a Role" card on My Account page

- ✓ Database migration backfills roles for all existing users

- ✓ Registration page branding update

v1.8.0–1.8.3 Feedback, Photo Upload & Polish February 21, 2026 ¦ COMPLETED

- ✓ Floating feedback button + admin review panel (64 items collected)

- ✓ Profile photo upload for all roles with auto-resize

- ✓ Message timestamps, 2FA tap-to-copy, care team invite flow

- ✓ Admin API key, SW network-first, APP_VERSION consistency

v1.6.0 Bug Fixes & Core UX February 20, 2026 ¦ COMPLETED

- ✓ Fixed Invalid Date in messages (timezone parsing)

- ✓ Locked down contact visibility (care team/assignment gated)

- ✓ Dashboard "Latest" status section, caregiver document review

- ✓ Medical care disclaimer modal (Virginia state law)

v1.4.0–1.5.7 Invites, Onboarding & Calendar February 19–20, 2026 ¦ COMPLETED

- ✓ Admin invite system, caregiver onboarding wizard (5-step)

- ✓ Calendar unification, care request system (requested → claimed)

- ✓ Email-first signup flow, caregiver onboarding hardening

- ✓ Self-service account deletion

v1.0.0–1.3.9 Auth, Care Teams, Location & Demo Mode February 18–19, 2026 ¦ COMPLETED

- ✓ Google OAuth, TOTP 2FA, trusted devices, demo mode isolation

- ✓ Care teams (CRUD, email invites, auto-creation, member management)

- ✓ Location-based caregiver search (Nominatim + Haversine)

- ✓ Availability engine, CaregiverCalendar, demo mode banner/switcher

- ✓ PWA icon overhaul, demo simplification (3 personas)

v0.1.0–0.9.0 Foundation February 15–18, 2026 ¦ COMPLETED

- ✓ Express API, PostgreSQL, JWT auth, 3 user roles

- ✓ Frontend modularization (17 components, zero-build-step)

- ✓ InPlace rebrand, PWA, mobile bottom nav, splash page

- ✓ WebSocket real-time updates, visit photos, analytics

- ✓ Recurring sessions, push notifications, shared care recipients

- ✓ Email verification, test suite (53 tests), rate limiting

# Future — AI-Powered Care Intelligence

Priority: HIGH — Core differentiator. Matching is the lead feature for sales and investor pitch.

## Why This Matters

Most care platforms are glorified job boards — families scroll, guess, and hope. AI matching turns InPlace into something fundamentally different: a system that understands care needs and finds the right person. This is the pitch: “Tell us about your loved one. We’ll find the right caregiver.” One sentence, zero browsing.

## Cost Analysis

AI API costs are per-call, based on tokens (roughly 1 token ≈ 0.75 words). At 100 active users, total AI cost is roughly $20–35/month. At 1,000 users, $150–300/month. At 10,000 users, $1,000–2,500/month. This is easily covered by the platform fee (15–20% of session cost). A single 3-hour session at $25/hr generates $11–15 in platform revenue — that covers ~2,000 AI matching calls.

Cost optimization levers:

- Prompt caching — 90% savings on repeated context. A cached match request drops from $0.005 to ~$0.001.

- Batch API — 50% discount for non-urgent tasks (weekly summaries, trend analysis).

- Model routing — Use cheaper models for simple tasks, reserve premium models for complex analysis.

- Result caching — Cache match results for same care-recipient profile for 24h.

AI-1: Intelligent Caregiver Matching (v2.5.0) Target: Q3 2026 ¦ PLANNED — Lead Feature

The headline feature. Family describes what they need → AI returns ranked caregivers with explanations.

- Care recipient conditions vs. caregiver specialties + stoplight preferences

- Schedule fit, past performance, distance, and rate compatibility

- Returns top 3–5 matches with plain-English explanations

- iPAi badge on AI-powered results for transparency

- Estimated effort: 2–3 days | Cost: <$5/month at current scale

AI-2: Session Note Intelligence (v2.6.0) Target: Q4 2026 ¦ PLANNED

Turn caregiver free-text notes into structured care insights.

- Extract structured data: mood, mobility, appetite, medication compliance, incidents

- Weekly/monthly care summaries for families with trend tracking

- Automated concern flags with push notifications to family

- Estimated effort: 3–4 days | Cost: $5–10/month

AI-3: Smart Scheduling & Demand Optimization (v2.7.0) Target: Q1 2027 ¦ PLANNED

Reduce empty caregiver hours. Reduce family costs. Increase platform revenue.

- Gap filling: proactive offers for caregiver downtime between sessions

- Demand-based rate suggestions, transparent to both sides

- Rebooking prompts and route-optimized scheduling for caregivers

- Estimated effort: 4–5 days | Cost: $3–8/month

AI-4: Proactive Engagement & Retention (v2.8.0) Target: Q2 2027 ¦ PLANNED

Keep families booking. Keep caregivers active. Reduce churn.

- Re-engagement nudges, caregiver burnout detection, review prompts

- Smart referral timing and onboarding coach for new caregivers

- Estimated effort: 3–4 days | Cost: <$5/month

AI-5: Family-Facing AI Assistant (v3.0.0) Target: Q3 2027 ¦ PLANNED — Long Game

Natural-language chat interface for families to ask about their loved one’s care.

- “How has Mom been this month?” “Which caregiver is best for overnight stays?”

- RAG system pulling from session history, visit notes, care profiles, caregiver data

- Estimated effort: 2–3 weeks | Cost: $15–30/month

## AI Implementation Notes

- Architecture: All AI calls through src/utils/ai.js — single abstraction layer with provider switching, retry logic, timeout, and cost logging.

- Graceful degradation: Every AI feature has a non-AI fallback (distance sort, manual browse, no summary).

- Privacy: No PII sent to AI APIs — names replaced with IDs. Care health data sent for matching but not stored by providers (zero-retention policies).

- iPAi branding: AI-powered results display an iPAi badge, letting users know they’re getting intelligent matching while keeping AI transparent and under the hood.

- Opt-out: Families can disable AI features in account settings.

# Pete’s Action Items

These unblock dev tasks above. Check them off as you go.

- Stripe: Add test API keys to Railway (sk_test_, pk_test_) → Unblocks v1.18.0

- Checkr: Sign up for partner account, get CHECKR_API_KEY → Unblocks v1.18.0

- Stripe: Decide background check price (Checkr ~$25–35)

- Plausible Analytics: Sign up at plausible.io, add yourinplace.com

- Google OAuth: Set up in Google Cloud Console (free)

- Google Maps API key (optional, later) — one-function swap

# User Feedback Summary

64 total feedback items collected from production (yourinplace.com) as of February 22, 2026.

| Category | Count |
| --- | --- |
| General | 31 |
| Bug | 15 |
| Feature | 11 |
| Complaint | 7 |

Key themes from new feedback: admin security (2FA gate), connection request UX, care recipient photos, payment fee model, caregiver signup validation, calendar visibility.

See FEEDBACK.md for full themed analysis and all 64 items.